CCEPD Self-Employment Project

(June 16, 2026)

Overview

The CCEPD’s Employment and Training Subcommittee is currently working on the topic of entrepreneurship and self-employment. At this time, they are collecting information and holding listening sessions.

Members have expressed interest in developing a toolkit addressing myth busting, expectation setting, scalability considerations, and connections to external resources applicable across DOR, DDS Regional Centers, and other workforce systems. The toolkit would focus on the preparation and early stages of self-employment for people with disabilities.

The subcommittee will work on the project throughout 2026, with the goal of completion and approval by the CCEPD’s first Full Committee Meeting held in 2027.

Timeline

The CCEPD would like to set an initial timeline of one year to complete this self-employment toolkit project. An approximate breakdown by month is below.

- February

  - Employment and Training Subcommittee (February 17)

    - Presentation from DOR’s Self Employment Program

- April

  - Employment and Training Subcommittee (April 21)

    - Presentation from DDS and Eastern Los Angeles Regional Center use of Paid Internship Program for micro enterprises and preparation for DOR’s Self Employment Program

- May

  - Employment and Training Subcommittee (May 19)

    - Discussion on next steps

- June

  - Employment and Training Subcommittee (June 16)

    - Presentation from Client Assistance Program (CAP) on Self-Employment

- July

  - Employment and Training Subcommittee (July 21)

    - Panel of DOR consumers involved with DOR’s Self Employment Program

- August

  - Employment and Training Subcommittee (August 18)

  - Discuss and determine specific topic areas within the early stages of self-employment for toolkit

- September

  - Employment and Training Subcommittee (September 15)

  - Develop specific topic areas within the early stages of self-employment for toolkit

- October

  - Employment and Training Subcommittee (October 20)

  - Continued development of specific topic areas within the early stages of self-employment for toolkit

- November

  - Employment and Training Subcommittee (November 17)

  - Continued development of specific topic areas within the early stages of self-employment for toolkit

- December

  - Employment and Training Subcommittee (December 15)

  - Subcommittee approval of self-employment toolkit

- January

  - Employment and Training Subcommittee (January 19)

  - CCEPD staff designs and formats self-employment toolkit

- February

  - CCEPD Full Committee approval of self-employment toolkit