## Active
COMMITTEE | DATE | ASSIGNED TO | ACTIVITY | DUE | STATUS | DONE | OUTCOME
Board | 2022-01-24 | TANYA | 2 - Review component list with DOR/Board 3 - Select team to develop components 4 - Develop components 5 - Partner current members with new members 6 - Roll out onboarding |  | 6/27: Met w/Megan; Scheduled onboarding for 7/14 6/15: Scheduled meetings for 6/20, 6/21 & 6/27 5/31: Scheduled planning meeting for 6/6 5/26: Send follow-up email, due 5/30 4/25: Send follow-up email, due 4/27 4/8: Sent follow-up email, due 4/8 3/30: Emailed Legal to determine if this has to be a public meeting - yes it must be noticed 4/5: Emailed Board to see who wants to be part of the team, due 4/7 |  | Yes - Daniel Yes - Eric No - Katie
Board | 2022-01-24 | BRANDY | 1 - review Nebraska’s by-laws to pull out data or formatting to include in ours 2 - review our by-laws to identify any edits to be made to language 3 - include additional information from Nebraska 4 - update our format 5 -Tanya review and edit 6 - Megan review and edit 7 - Board to review and comment 8 - prepare final draft for Board approval 9 - Board approves at July meeting |  | 6/15: Drafted steps and assigned to Brandy 3/30: Received Nebraska's by-laws from Dan 4/5: Discuss at the April Board meeting, emailed to the Board
Board | 2022-01-24 | DOR | continue to work on the formatting of the State Plan | 2022-07-18 | 5/23: Tentative approval at the Board meeting 4/25: Sent final draft to update at May meeting
Board | 2022-05-23 | BRANDI | post HARC report to web | 2022-06-07 | 6/28: Brandi will submit again to IT 6/24:Texted Brandi to f/u 6/20:Brandi requested 6/16: Requested Brandy post to internet 6/15: Tanya's copy shows accessibility issues but Brandy's does not
Board | 2022-05-23 | DOR | share State Plan with Board | 2022-07-01
Board | 2022-05-23 | DOR | determine process for the public to become committee members | 2022-06-30 | Put on hold until 2023 per Megan
Board | 2022-07-18 | DOR | Send out meeting minutes and activity tracker | 2022-07-19
Board | 2022-07-18 | DOR | Send out the Registry presentation | 2022-07-29
Board | 2022-07-18 | DOR | Send out the HARC infographic | 2022-07-29
Board | 2022-07-18 | DOR | Send out list of potential distribution outlets for the State Plan
Board | 2022-07-18 | DOR | Coordinate new committee assignments and meeting schedule | 2022-07-22
Board | 2022-07-18 | DOR | Send out NASHIA Conference information | 2022-07-22
State Plan | 2022-02-08 | Megan | ask TARC to review the State Plan | 2022-02-15 | 6/14: Has been sent to Judy already
State Plan | 2022-06-14 | DOR | send the current plan version to members | 2022-07-01
State Plan | 2022-06-14 | DOR | share the list of TBI sites that are funded by DOR | 2022-06-17 | 6/22: Asked Brandi if she has a list already
State Plan | 2022-06-14 | DOR | look into a recording of HARC’s presentation at the Board meeting | 2022-06-17 | 6/20: Trying to figure out how to pull the presentation from Zoom recording
Sustainable Funding | 2022-01-11 | Daniel | research SB855 and CDPH for potential funding |  | SB855: an expansion of the CA Mental Health Parody proposed by Democrat Scott Weiner, sign by Governor Newsom in Sept '21; effective 1/1/22. Expands coverage to neurocognitive disorder due to TBI. 6/2: Megan emailed Daniel back 5/28: Daniel emailed to get a contact at DMHC 1/11: Daniel would like assistance
Sustainable Funding | 2022-02-08 | Tanya | reach out to Victor Duron (homeless) |  | 4/5: Connect again closer to year end 3/30: Emailed Victor, replied
Sustainable Funding | 2022-03-11 | Daniel | Look into Diversity Equity Inclusion Initiative for funding |  | 6/21: Emailed Daniel for update

## 2022 Completed
COMMITTEE | DATE | ASSIGNED TO | ACTIVITY | DUE | STATUS | DONE | OUTCOME
Registry | 2021-10-18 | Henry | explore Maryland, Massachusetts, Minnesota and Missouri's registries online |  | Completed | 2022-01-11 | State registry sites are quite variable; only Maryland had a site specific to TBI but with no registry data; other State sites were joint with trauma; links and specifics are saved in the 'G' drive
State Plan | 2022-01-11 | Lili | draft language for pediatrics and children for future focus |  | Completed | 2022-01-11 | Lili submitted the draft to DOR
Sustainable Funding | 2022-02-08 | Todd | research private foundations, Developmental Services and Universty Centers for Excellence in Developments Disabilities for potential funding |  | Completed | 2022-01-11 | Unable to find current TBI projects
State Plan | 2022-01-11 | Chuck | draft the 'Veterans/Military' Future Area of Focus |  | Completed | 2022-01-13 | Chuck submitted his draft to DOR
State Plan | 2022-01-11 | DOR | forward resources to assist with Future Areas of Focus to all members |  | Completed | 2022-01-14 | Megan forwarded NASHIA conference matierals
Registry | 2021-10-18 | Eric | explore Alaska and Arkansas's registries online |  | Completed | 2022-01-20 | Eric sent to DOR, DOR sent to committee
Registry | 2022-01-11 | DOR | share the prior questions asked of other States |  | Completed | 2022-01-21 | Tanya forwarded to committee
State Plan | 2022-01-11 | DOR | send Lili Georgia's State Plan |  | Completed | 2022-01-21 | Tanya sent the plan
Board | 2022-01-24 | DOR | send action items to Board members after the meeting |  |  | 2022-01-24 | Sent to members at end of meeting
Board | 2022-01-24 | Daniel | send DOR the most current questions for CalSpeaks |  |  | 2022-01-24 | Sent to Tanya/Brandi/Megan
Board | 2022-01-24 | Daniel | send a clear definition of TBI versus ABI to DOR to be included in the State Plan |  |  | 2022-02-02 | Sent to Tanya/Brandi/Megan
Board | 2022-01-24 | DOR | send Board members the ‘Release of Information’ form for survivor stores, quotes and photos | N/A |  | 2022-03-30 | Two forms were sent to the Board members for quotes and/or photos
Board | 2022-01-24 | DOR | add Daniel to the Needs Assessment committee meetings through May 2022 | N/A |  | 2022-03-30 | Daniel has been attending as a member of te public and that is working well, no need to officially add him at this time
Board | 2022-01-24 | DOR | send out the revised by-laws for review and discussion at the April Board meeting |  |  | 2022-03-30 | Sent to Board members for voting at the April Board meeting
Needs Assessment | 2022-01-11 | DOR | look into setting up a survey where language can be selected by the survey taker |  | No longer needed | 2022-02-08 | No longer needed as HARC received the contract
Needs Assessment | 2022-01-11 | DOR | find out if DOR has the ability to produce surveys in multiple languages |  | No longer needed | 2022-02-08 | No longer needed as HARC received the contract
Needs Assessment | 2022-01-11 | DOR | find out if non-members can assist with NA survey |  | No longer needed | 2022-02-08 | No longer needed as HARC received the contract
Needs Assessment | 2022-01-11 | DOR | schedule weekly NA meetings if the NA survey needs to be done in-house |  | No longer needed | 2022-02-08 | No longer needed as HARC received the contract
Needs Assessment | 2022-02-08 | Chuck | draft an email to the Board for distribution outlets for survey | 2022-02-11 | Completed | 2022-02-15 | Sent draft email
Needs Assessment | 2022-02-08 | DOR | ask the Board for distribution outlets for survey | 2022-02-15 | Completed | 2022-02-25 | Brandi sent email
Needs Assessment | 2022-01-11 | DOR | invite the Board member applicants to the April Board meeting |  | Completed | 2022-03-01 | All applicants were sent a calendar invitation
Needs Assessment | 2022-03-11 | Tanya | invite HARC to attend all Committee meetings | 2022-03-01 |  | 2022-03-08 | Will attend all committee meetings
Needs Assessment | 2022-01-11 | DOR | verify the tangible product ACL is expecting |  |  | 2022-03-09 | Submit survey, interview guide and results (if received)
Needs Assessment | 2022-02-08 | DOR | work with HARC to finalize a project timeline | 2022-02-18 |  | 2022-03-09 | Sent timeline to committee
Needs Assessment | 2022-02-08 | DOR | ask HARC to attend all Committee meetings | 2022-02-11 | 3/9: Only invited to March so far | 2022-03-11 | HARC agreed to attend all meetings
Needs Assessment | 2022-03-11 | Brandi | obtain the surveys from HARC | 2022-03-13 |  | 2022-03-11 | Sent to Brandi/Tanya/Megan/Chuck/Susan
Needs Assessment | 2022-03-11 | Tanya | complete today’s meeting minutes and distribute | 2022-03-18 |  | 2022-03-11 | Sent to members at end of meeting
Needs Assessment | 2022-03-11 | Members | work with HARC to finalize the survey | 2022-03-16 |  | 2022-03-22 | Survey finalized to be published 3/28/22
Needs Assessment | 2022-03-11 | Tanya | invite HARC to April Board meeting | 2022-03-16 |  | 2022-03-30 | Will attend the April Board meeting
Registry | 2022-01-11 | DOR | send the Best Practices for Using TBI Registries to Connect People: A National Guide |  |  | 2022-03-09 | Sent in October 2021 Emailed to committee again in March 2022
Registry | 2022-03-11 | Tanya | complete today’s meeting minutes and distribute | 2022-03-16 |  | 2022-03-11 | Sent to members at end of meeting
Registry | 2022-03-11 | Tanya | send Dan Clark the Best Practices for Using TBI Registries to Connect People: A National Guide | 2022-03-16 |  | 2022-03-30 | Sent to Dan
State Plan | 2022-01-11 | Steven | send the State Plan committee notes about ILC-homeless from the 10/12/21 meeting |  | Not completed | 2022-02-08 | Could not find notes
State Plan | 2022-01-11 | Members | provide comments/edits of the state Plan to DOR |  | Completed | 2022-02-08 | No feedback received
State Plan | 2022-02-08 | DOR | send the current plan version to members | 2022-02-11 | Completed | 2022-02-14 | Megan sent draft to committee
State Plan | 2022-01-11 | DOR | correct December's meeting minutes and post to internet |  | Completed | 2022-02-23 | Corrected minutes posted
State Plan | 2022-01-11 | DOR | finalize the new project tracking tool | 2022-02-01 | Completed | 2022-03-01 | Sent to Committees for review at March 2022 meeting
State Plan | 2022-01-11 | Megan | review the accessibility of the new State Plan format |  | Completed | 2022-03-01 | Megan sent out an accessible format to Board members for review
State Plan | 2022-01-11 | DOR | send the 19/20 State TBI annual report to all members | 2022-02-11 | Completed | 2022-03-07 | DOR sent report to State Plan members
State Plan | 2022-02-08 | Members | provide comments/edits of the state Plan to DOR | 2022-03-04 | 3/9: Sent email reminder to committee | 2022-03-10 | 3/2: Chuck 3/8: Dan
State Plan | 2022-01-11 | Steven | draft language for the CA TBI Advisory Board history/current section | TBD | Discuss at Mar meeting | 2022-03-11 | No longer needed
State Plan | 2022-02-08 | Tanya | send the release form for consumers | 2022-02-11 |  | 2022-03-30 | Sent to Board members
Sustainable Funding | 2022-02-08 | Lili | research Drug and Alcohol Rehabilitation funding |  | 3/11: Per Katie, there are many funds for rehab but are not specific to TBI 1/11: Lili will compile a list of options, there are a lot of options | 2022-03-11 | Not an ideal funding but maybe a great partnership
Sustainable Funding | 2022-01-11 | Katie | research other ACL grants |  |  | 2022-03-11 | Nothng specific to TBI at this time
Sustainable Funding | 2022-01-11 | DOR | update all Board members on Board member recruitment and Survivor committee |  |  | 2022-03-11 | Updates were provided at the March committee meeting
Sustainable Funding | 2022-02-08 | Jack | look into a budget ask |  | 3/11: This requires a lot of work and has a long lead time, this can be an ongoing funding source to pursue - Board can make a recommendation to DOR | 2022-03-11 | The committee decided to pursue a BCP
Sustainable Funding | 2022-03-11 | Tanya | complete today’s meeting minutes and distribute | 2022-03-16 |  | 2022-03-11 | Sent to members at the end of the meeting
Sustainable Funding | 2022-01-11 | Tanya | see if we have have received a list of funding sources from other States | 2022-03-18 |  | 2022-03-30 | Final TBI Funding Primer 05.29.20
Board | 2022-01-24 | DOR | add to the February committee agenda, skills sets for each committee and revising the Executive committee duties |  |  | 2022-03-29 | Added to the April Board meeting
Needs Assessment | 2022-03-11 | Brandi | send the Board information on participating in the HARC interviews | 2022-03-16 |  | 2022-03-18 | Sent with HARC weekly update
Registry | 2021-12-14 | Brandi | pursue the BCUP process to obtain data from OSHPD | Ongoing |  | 2022-01-10
Registry | 2022-02-08 | Tanya | distribute the CalSpeaks Code Book to the committee | 2022-03-16 |  | 2022-04-05 | Sent to Registry Committee
Registry | 2022-02-08 | Daniel | send DOR the CalSpeaks Code Book | 2022-02-11 |  | 2022-02-11
State Plan | 2022-03-11 | Megan | send the current plan version to members | 2022-03-16 |  | 2022-03-18 | Sent to the Board members
Registry | 2022-01-11 | Brandi | explore Kansas's registry online |  | 3/11/22: Scheduling two meetings in the next few weeks | 2022-04-05 | They use the State Waiver program and then have the ADRC as there assessment center and then from there they navigate services
Board | 2022-01-24 | Members | send DOR potential outlets to disseminate the needs assessment surveys to survivors |  | 3/9 & 4/1: Asked Brandi to send reminder | 2022-03-31 | 2/28: Henry 3/2: Katie, Susan 3/3: Eric 3/30: Daniel
Needs Assessment | 2022-01-11 | Members | provide DOR outlets for survey dissemination |  | 3/9 & 4/1: Asked Brandi to send reminder | 2022-03-31 | 2/28: Henry 3/2: Katie, Susan 3/3: Eric 3/30: Daniel
State Plan | 2022-03-11 | Members | provide state plan draft comments/edits to DOR | 2022-04-05 | 4/5: Emailed reminder to Committee | 2022-04-22 | 4/6: Received: Henry
State Plan | 2022-01-11 | Megan | create a mission statement and summary for the Survivor committee | TBD | 3/3: First meeting was held, next meeting is 3/15/22 | 2022-04-25 | Per Megan, has been updated
State Plan | 2022-03-11 | Megan | discuss developing a mission statement for the entire CA TBI program | 2022-04-05 |  | 2022-04-25 | Per Megan, has been updated
Sustainable Funding | 2022-01-11 | Megan | research HCBS and Aging for potential funding |  | 3/11: Have $5 million from HCBS; cannot talk about agining yet | 2022-04-25 | HCBS is already implemented
State Plan | 2022-03-11 | Tanya | connect with CATBI to collect consumer narrative/photos | 2022-04-05 | 4/6: Asked Katie to send an email to CATBI - sent 4/8 4/5: Emailed Katie and Daniel for guidance | 2022-05-06 | Received enough quotes/photos
Board | 2022-01-24 | Members | send survivor stories, quotes and photos to DOR to be included in the State Plan |  |  | 2022-05-23 | No longer applicable as photos will not be added
Board | 2022-05-23 | DOR | send 2021 SPP narrative and committee info to Board | 2022-05-30 |  | 2022-05-26 | Sent to Board and Dan Clark
Registry | 2022-01-11 | Members | review the Best Practices for Using TBI Registries to Connect People: A National Guide |  | 3/11/22: Everyone has reviewed except Steve (not in mtg today) | 2022-05-06
State Plan | 2022-05-06 | DOR | send the current plan version to members | 2022-05-17 |  | 2022-05-17
State Plan | 2022-05-06 | Susan & Brandi | add consumer quotes and photos | 2022-05-16 |  | 2022-06-14 | No longer using photos, but will use quotes
Needs Assessment | 2022-02-08 | Brandi | forward HARC's updates to the Committee every Friday starting 2/18/22 | Fridays | Ongoing | 2022-05-27
Registry | 2021-10-18 | Katie | explore Colorado and Georgia's registries online |  | 3/11/22: Katie will send notes for Colorado 1/11/22: Georgia is done - not much and is included with their trauma registry, Colorado is, Katie will send notes for Georgia | 2022-06-14 | Not Longer Relevent
Registry | 2021-10-18 | Steven | explore Idaho's and Iowa's registries online |  | 1/11/22: Ongoing | 2022-06-14 | Not Longer Relevent
Registry | 2022-01-11 | Tanya | prepare a state list of who has a registry, link to registry, came to a registry meeting and had best practices in place | 2022-03-18 | 4/6: Emailed Judy - received 4/11 3/11: NASHIA has a list like this | 2022-06-14 | Not Longer Relevent
Registry | 2022-01-11 | Members | review the TBI in the U.S. Future of Registries and Data Systems Guide |  |  | 2022-06-14 | Not Longer Relevent
Registry | 2022-01-11 | Chuck | reach out to MSKTC |  | 3/11/22: Will complete | 2022-06-14 | Not Longer Relevent
Registry | 2022-02-08 | Daniel | provide Alabama and Nebraska's registry reviews | 2022-02-18 |  | 2022-06-14 | Not Longer Relevent
Board | 2022-05-23 | HARC | final report | 2022-05-31 |  | 2022-05-31
Board | 2022-05-23 | DOR | share HARC report with Board | 2022-06-07 |  | 2022-06-08
Sustainable Funding | 2022-01-11 | Lili | research other federal funding sources |  | 1/11: Lili will compile a list of options | 2022-06-14 | No longer applicable
State Plan | 2022-05-06 | Chuck | finalize the ‘Needs Assessment’ section after the final report is received from HARC | 2022-06-10 |  | 2022-06-21 | Megan completed this