## Active
California Traumatic Brain Injury Advisory Committees
Activity Tracker
COMMITTEE | DATE | ASSIGNED TO | ACTIVITY | DUE | STATUS | DONE | OUTCOME
State Plan | 2022-01-11 | Megan | create a mission statement and summary for the Survivor committee | TBD | 3/3: First meeting was held
State Plan | 2022-01-11 | Steven | draft language for the CA TBI Advisory Board history/current section | TBD | Discuss at Feb meeting
State Plan | 2022-02-08 | Tanya | send the release form for consumers | 2022-02-11
State Plan | 2022-02-08 | DOR | ask TARC to review the State Plan | 2022-02-15 | Judy will review after the Board has provided a conditional approval in April
State Plan | 2022-02-08 | Members | provide comments/edits of the state Plan to DOR | 2022-03-04 | 3/9: Sent email reminder to committee |  | 3/2: Chuck 3/8: Dan
State Plan | 2022-02-08 | Steven | draft language for the CA TBI Advisory Board current section to include data from RFA | TBD
Needs Assessment | 2022-01-11 | Members | provide DOR outlets for survey dissemination |  | 3/9: Asked Brandi to send reminder |  | 2/28: Henry 3/2: Katie, Susan 3/3: Eric
Needs Assessment | 2022-02-08 | DOR | forward HARC's updates to the Committee every Friday starting 2/18/22 | Fridays | 3/9: Sent 3/4 email
Needs Assessment | 2022-02-08 | DOR | ask HARC to attend all Committee meetings | 2022-02-11 | 3/9: Only invited to March so far
Needs Assessment | 2022-02-08 | DOR | invite HARC to April Board meeting | 2022-02-11
Registry | 2022-01-11 | DOR | explore Kansas's registry online
Registry | 2022-01-11 | DOR | prepare a state list of who has a registry, link to registry, came to a registry meeting and had best practices in place
Registry | 2021-10-18 | Katie | explore Colorado and Georgia's registries online |  | 1/11/22: Georgia is done, Colorado is in progress, Katie will send notes for Georgia
Registry | 2021-10-18 | Steven | explore Idaho's and Iowa's registries online |  | 1/11/22: Ongoing
Registry | 2021-12-14 | DOR | pursue the BCUP process to obtain data from OSHPD | 2022-01-04
Registry | 2022-01-11 | Members | review the Best Practices for Using TBI Registries to Connect People: A National Guide
Registry | 2022-01-11 | Members | review the TBI in the U.S. Future of Registries and Data Systems Guide
Registry | 2022-01-11 | Megan | reach out to MSKTC
Registry | 2022-02-08 | DOR | explore Kansas's registry online | 2022-02-25
Registry | 2022-02-08 | DOR | send the TBI in the U.S. Future of Registries and Data Systems Guide | 2022-02-11
Registry | 2022-02-08 | DOR | distribute the CalSpeaks Code Book to the committee | 2022-02-15
Registry | 2022-02-08 | Daniel | provide Alabama and Nebraska's registry reviews | 2022-02-18
Registry | 2022-02-08 | Members | will review the Best Practices for Using TBI Registries to Connect People: A National Guide | 2022-03-10
Registry | 2022-02-08 | Members | will review the TBI in the U.S. Future of Registries and Data Systems Guide | 2022-03-10
Registry | 2022-02-08 | Daniel | send DOR the CalSpeaks Code Book | 2022-02-11
Sustainable Funding | 2022-01-11 | DOR | see if we have have received a list of funding sources from other States
Sustainable Funding | 2022-01-11 | DOR | update all Board members on Board member recruitment and Survivor committee
Sustainable Funding | 2022-01-11 | Megan | research HCBS and Aging for potential funding
Sustainable Funding | 2022-01-11 | Daniel | research SB855 and CDPH for potential funding |  | SB855: an expansion of the CA Mental Health Parody proposed by Democrat Scott Weiner, sign by Governor Newsom in Sept '21; effective 1/1/22. Expands coverage to neurocognitive disorder due to TBI. 1/11: Daniel would like assistance
Sustainable Funding | 2022-01-11 | Lili | research other federal funding sources |  | 1/11: Lili will compile a list of options
Sustainable Funding | 2022-01-11 | Katie | research other ACL grants
Sustainable Funding | 2022-02-08 | DOR | reach out to Victor Duron (homeless)
Sustainable Funding | 2022-02-08 | Lili | research Drug and Alcohol Rehabilitation funding |  | 1/11: Lili will compile a list of options, there are a lot of options
Sustainable Funding | 2022-02-08 | Jack | look into a budget ask
Board | 2022-01-24 | DOR | send Board members the ‘Release of Information’ form for survivor stores, quotes and photos
Board | 2022-01-24 | DOR | add Daniel to the Needs Assessment committee meetings through May 2022
Board | 2022-01-24 | DOR | schedule a meeting to develop the Board member onboarding and orientation materials and process
Board | 2022-01-24 | DOR | add to the February committee agenda, skills sets for each committee and revising the Executive committee duties
Board | 2022-01-24 | DOR | send out the revised by-laws for review and discussion at the April Board meeting
Board | 2022-01-24 | DOR | review Nebraska’s by-laws and update our format
Board | 2022-01-24 | DOR | send action items to Board members after the meeting
Board | 2022-01-24 | DOR | continue to work on the formatting of the State Plan
Board | 2022-01-24 | Daniel | send DOR the most current questions for CalSpeaks
Board | 2022-01-24 | Daniel | send a clear definition of TBI versus ABI to DOR to be included in the State Plan
Board | 2022-01-24 | Members | send DOR potential outlets to disseminate the needs assessment surveys to survivors
Board | 2022-01-24 | Members | send survivor stories, quotes and photos to DOR to be included in the State Plan

## 2022 Completed
California Traumatic Brain Injury Advisory Committees
Activity Tracker - Completed Activities
COMMITTEE | DATE | ASSIGNED TO | ACTIVITY | DUE | STATUS | DONE | OUTCOME
Registry | 2021-10-18 | Henry | explore Maryland, Massachusetts, Minnesota and Missouri's registries online |  | Completed | 2022-01-11 | State registry sites are quite variable; only Maryland had a site specific to TBI but with no registry data; other State sites were joint with trauma; links and specifics are saved in the 'G' drive
State Plan | 2022-01-11 | DOR | finalize the new project tracking tool | 2022-02-01 | Completed | 2022-03-01 | Sent to Committees for review at March 2022 meeting
State Plan | 2022-01-11 | Chuck | draft the 'Veterans/Military' Future Area of Focus |  | Completed | 2022-01-13 | Chuck submitted his draft to DOR
State Plan | 2022-01-11 | Lili | draft language for pediatrics and children for future focus |  | Completed | 2022-01-11 | Lili submitted the draft to DOR
State Plan | 2022-01-11 | Megan | review the accessibility of the new State Plan format |  | Completed | 2022-03-01 | Megan sent out an accessible format to Board members for review
Needs Assessment | 2022-01-11 | DOR | invite the Board member applicants to the April Board meeting |  | Completed | 2022-03-01 | All applicants were sent a calendar invitation
State Plan | 2022-01-11 | DOR | correct December's meeting minutes and post to internet |  | Completed | 2022-02-23 | Corrected minutes posted
State Plan | 2022-01-11 | DOR | send Lili Georgia's State Plan |  | Completed | 2022-01-21 | Tanya sent the plan
State Plan | 2022-01-11 | DOR | forward resources to assist with Future Areas of Focus to all members |  | Completed | 2022-01-14 | Megan forwarded NASHIA conference matierals
State Plan | 2022-01-11 | DOR | send the 19/20 State TBI annual report to all members | 2022-02-11 | Completed | 2022-03-07 | DOR sent report to State Plan members
State Plan | 2022-01-11 | Steven | send the State Plan committee notes about ILC-homeless from the 10/12/21 meeting |  | Not completed | 2022-02-08 | Could not find notes
State Plan | 2022-01-11 | Members | provide comments/edits of the state Plan to DOR |  | Completed | 2022-02-08 | No feedback received
State Plan | 2022-02-08 | DOR | send the current plan version to members | 2022-02-11 | Completed | 2022-02-14 | Megan sent draft to committee
Needs Assessment | 2022-01-11 | DOR | look into setting up a survey where language can be selected by the survey taker |  | No longer needed | 2022-02-08 | No longer needed as HARC received the contract
Needs Assessment | 2022-01-11 | DOR | find out if DOR has the ability to produce surveys in multiple languages |  | No longer needed | 2022-02-08 | No longer needed as HARC received the contract
Needs Assessment | 2022-01-11 | DOR | find out if non-members can assist with NA survey |  | No longer needed | 2022-02-08 | No longer needed as HARC received the contract
Needs Assessment | 2022-01-11 | DOR | schedule weekly NA meetings if the NA survey needs to be done in-house |  | No longer needed | 2022-02-08 | No longer needed as HARC received the contract
Needs Assessment | 2022-02-08 | Chuck | draft an email to the Board for distribution outlets for survey | 2022-02-11 | Completed | 2022-02-15 | Sent draft email
Needs Assessment | 2022-02-08 | DOR | ask the Board for distribution outlets for survey | 2022-02-15 | Completed | 2022-02-25 | Brandi sent email
Registry | 2022-01-11 | DOR | share the prior questions asked of other States |  | Completed | 2022-01-21 | Tanya forwarded to committee
Registry | 2021-10-18 | Eric | explore Alaska and Arkansas's registries online |  | Completed | 2022-01-20 | Eric sent to DOR, DOR sent to committee
Sustainable Funding | 2022-02-08 | Todd | research private foundations, Developmental Services and Universty Centers for Excellence in Developments Disabilities for potential funding |  | Completed | 2022-01-11 | Unable to find current TBI projects
Needs Assessment | 2022-01-11 | DOR | verify the tangible product ACL is expecting |  |  | 2022-03-09 | Submit survey, interview guide and results (if received)
Registry | 2022-01-11 | DOR | send the Best Practices for Using TBI Registries to Connect People: A National Guide |  |  | 2022-03-09 | Sent in October 2021 Emailed to committee again in March 2022
Needs Assessment | 2022-02-08 | DOR | work with HARC to finalize a project timeline | 2022-02-18 |  | 2022-03-09 | Sent timeline to committee